## Sheet1
Project Name | GPM
Project Manager | Martin Stobbelaar, Edah Sahinovic
Project Deliverable | ArcGIS Dashboard
Start Date | 2022-10-28
End Date | 2023-01-24
Overall Progress | 90%
Tasks | Responsible | Start | End | Days | Status | 21.11.2022 - 27.11.2022 | [6 empty] | 28.11.2022 - 04.12.2022 | [6 empty] | 05.12.2022 - 11.12.2022 | [6 empty] | 12.12.2022 - 18.12.2022 | [6 empty] | 19.12.2022 - 25.12.2022 | [6 empty] | 26.12.2022 - 01.01.2023 | [6 empty] | 02.01.2023 - 08.01.2023 | [6 empty] | 09.01.2023 - 15.01.2023 | [6 empty] | 16.01.2023 - 22.01.2023
WP 1: Project Management | [5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Kick-off meeting (set-up) | Martin Stobbelaar, Edah Sahinovic | 2022-11-24 | 2022-11-24 | 0 | Complete | 26.12.2022 - 01.01.2023 M: Christmass break week
Project Documentation | Edah Sahinovic | 2022-11-24 | 2022-12-02 | 8 | Completed
Data search | Martin Stobbelaar, Edah Sahinovic | 2022-11-25 | 2022-11-29 | 4 | Completed
WP 2: Data Acquisition | bar: 21.11.2022 - 27.11.2022 M to 19.12.2022 - 25.12.2022 S; 02.01.2023 - 08.01.2023 M to 16.01.2023 - 22.01.2023 S
Organize gathered data | Martin Stobbelaar | 2022-12-01 | 2022-12-07 | 6 | Completed
Implement data to database | Martin Stobbelaar, Edah Sahinovic | 2022-12-05 | 2022-12-12 | 7 | Completed
Altering shapefiles | Martin Stobbelaar, Edah Sahinovic | 2022-12-05 | 2022-12-12 | 7 | Completed
Additional data work | Martin Stobbelaar, Edah Sahinovic |  |  | 0 | Completed
WP 3: Data processing | bar: 21.11.2022 - 27.11.2022 M to 19.12.2022 - 25.12.2022 S; 02.01.2023 - 08.01.2023 M to 16.01.2023 - 22.01.2023 S
Processing and merging data | Martin Stobbelaar, Edah Sahinovic | 2022-12-10 | 2022-12-16 | 6 | Completed
Creating metadata | Martin Stobbelaar | 2022-12-10 | 2022-12-22 | 12 | Completed
Publishing | Martin Stobbelaar, Edah Sahinovic | 2022-12-16 | 2023-01-03 | 18 | Completed
WP 4: Dashboards Development | bar: 21.11.2022 - 27.11.2022 M to 19.12.2022 - 25.12.2022 S; 02.01.2023 - 08.01.2023 M to 16.01.2023 - 22.01.2023 S
Setting up the SDI | Martin Stobbelaar, Edah Sahinovic | 2022-12-25 | 2023-01-06 | 12 | Completed
Creating dashboards | Martin Stobbelaar, Edah Sahinovic | 2023-01-02 | 2023-01-09 | 7 | Completed
Optimizing | Martin Stobbelaar, Edah Sahinovic | 2023-01-07 | 2023-01-15 | 8 | Completed
WP 5: Project Presentation | bar: 21.11.2022 - 27.11.2022 M to 19.12.2022 - 25.12.2022 S; 02.01.2023 - 08.01.2023 M to 16.01.2023 - 22.01.2023 S
Project (final) presentation | Martin Stobbelaar, Edah Sahinovic | 2023-01-15 | 2023-01-24 | 9 | Completed
Submission of project | Martin Stobbelaar, Edah Sahinovic | 2023-01-25 | 2023-02-15 | 21 | In progress
Launch |  | 2023-02-15 | bar: 21.11.2022 - 27.11.2022 M to 19.12.2022 - 25.12.2022 S